## Sheet1
ID | story | ww 1 | WW 2 | WW 3 | WW 4 | WW 5 | WW 6 | WW 7 | WW 8 | WW 9 | WW 10 | WW 11 | WW 12 | WW 13 | WW 14 | WW 15 | WW 16 | WW 17 | WW 18 | WW 19 | WW 20 | WW 21 | WW 22 | WW 23 | WW 24 | WW 25 | WW 26 | WW 27 | WW 28 | WW 29 | WW 30 | Work Week number
|  | 13.11 | 20.11 | 27.11 | 4.12 | 11.12 | 18.12 | 25.12 | 1.01 | 8.01 | 15.01 | 22.01 | 29.01 | 5.02 | 12.02 | 19.02 | 26.02 | 4.03 | 11.03 | 18.03 | 25.03 | 1.04 | 8.04 | 15.04 | 22.04 | 29.04 | 6.05 | 13.05 | 20.05 | 27.05 | 3.06 | beginning of the week date
1 | study and learn the google app engine | bar: ww 1 to WW 4
2 | development admin side | bar: WW 5 to WW 10
2.1 | * manage missions | bar: WW 5 to WW 7
2.2 | * manage qustinure | bar: WW 8 to WW 10
2.3 | * web statistics | bar: WW 5 to WW 7
2.4 | * mange users: add ban free to user | bar: WW 8 to WW 10
3 | development client side | bar: WW 11 to WW 18
3.1 | * regestration proccess (landing page) | bar: WW 11 to WW 18
3.1.1 | ** Registration Using Facebook | bar: WW 11 to WW 12
3.1.2 | ** Registration From Scratch | bar: WW 11 to WW 12
3.1.3 | ** Create a wish list | bar: WW 13 to WW 14
3.1.4 | ** Circle of Happiness questionaire | bar: WW 13 to WW 14
3.1.5 | ** Manage Friends List | bar: WW 15 to WW 18
3.2 | * home page | bar: WW 15 to WW 30
3.2.1 | ** Module of Circle of Happiness | bar: WW 15 to WW 16
3.2.2 | ** Module of Open missions | bar: WW 19 to WW 20
3.2.3 | ** Module of Friends Missions | bar: WW 17 to WW 18
3.2.4 | ** Module of Completed Missions | bar: WW 21 to WW 22
3.2.5 | ** Module of friends | bar: WW 23 to WW 24
3.2.6 | ** Edit profile page | bar: WW 19 to WW 21
3.2.7 | ** Tip Bank page | bar: WW 24 to WW 25
3.2.8 | ** Missions page | bar: WW 25 to WW 26
3.2.9 | ** A Friend’s Mission page - add comments | bar: WW 26 to WW 28
3.2.10 | ** Consult With a Friend | bar: WW 28 to WW 30
3.2.11 | ** mission lifecycle and process | bar: WW 27 to WW 30
mater task - which igor & michael are doing
small task - which Michael doiing
small task - which Igor is doing